## Agile Product Backlog
AGILE PRODUCT BACKLOG TEMPLATE
PBID | ROLE | I WANT TO BE ABLE TO | SO THAT | SPRINT # | ASSIGNED TO | PRIORITY | STORY POINTS
|  | Personalized Music Recommendations | The "SO THAT" column was left blank for user stories because the intended goal is already stated in the "I WANT TO BE ABLE TO" column. | Sprint 1 | Rinor Kastrati | High | 61
1 |  | As a user, I want to receive personalized music recommendations based on my listening history and preferences. |  |  | " " | Medium | 8 | This section is for the drop-down list
2 |  | As a user, I want to be able to customize my music recommendations by genre, mood, and tempo. |  |  |  | Medium | 13 | Yes | High | Complete
3 |  | As a user, I want to be able to share my music recommendations with friends and on social media. |  |  |  | High | 21
4 |  | As a user, I want to be able to listen to full tracks for recommended music. |  |  |  | Medium | 8
5 |  | As a user, I want to be able to save my favorite tracks and view them later. |  |  |  | Medium | 8
6 |  | As a user, I want to be able to search for specific tracks or artists. |  |  |  | Low | 3
|  | Music Sharing and Social Features |  |  | Rinor Kastrati | High | 50 |  |  | Not Started
|  | As a user, I want to be able to create and share playlists with friends and followers. I want to curate a collection of music for others to enjoy. |  |  |  | Medium | 13
|  | As a user, I want to be able to follow and connect with other music enthusiasts. I want to discover new music and connect with like-minded people |  |  |  | Medium | 8
|  | As a user, I want to be able to discover new music and playlists based on what my friends and followers are listening to. I want to expand my music library and discover new artists. |  |  |  | Low | 5
|  | As a user, I want to be able to create and participate in music-related groups and events. I want to connect with people who share my musical interests and attend music-related events |  |  |  | Medium | 13
|  | As a user, I want to be able to share my favorite lyrics and quotes from songs on social media. I want to express my love for music and connect with others who appreciate it |  |  |  | Low | 3
|  | As a user, I want to be able to collaborate with friends to create playlists and share music. I want to share my music preferences with friends and discover new music through them. |  |  |  | Medium | 8
|  | User profile Management |  |  | Rinor Kastrati | High | 63
|  | As a user, I want to be able to create and customize my profile. |  |  |  | High | 21
|  | As a user, I want to be able to connect with friends and view their profiles. |  |  |  | Medium | 13
|  | As a user, I want to be able to manage my privacy settings. |  |  |  | Medium | 13
|  | As a user, I want to be able to view and manage my activity feed. |  |  |  | Low | 3
|  | As a user, I want to be able to view and manage my saved items. |  |  |  | Low | 5
|  | As a user, I want to be able to view and manage my notifications. |  |  |  | Medium | 8

## Tasks
| BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW | Ne baze te linkut ne vijim definohen story points
User Story | As a user, I want to receive personalized music recommendations based on my listening history and preferences. | 8 | Fullstack Dev | Not Started | 4h | [5 empty] | Pending | https://www.tothenew.com/blog/how-to-estimate-story-points-in-agile/
1 | Research and integrate a machine learning algorithm for music recommendations
2 | Design and implement a user preference survey
3 | Develop a system for tracking user listening history
4 | Implement a user interface for displaying recommended music
5 | Test recommendation algorithm and adjust as necessary
6 | Implement system for refreshing recommendations periodically
User story | As a user, I want to be able to customize my music recommendations by genre, mood, and tempo | 13 | Fullstack Dev | Not Started | 8h | [5 empty] | Pending
1 | Develop user preference options for genre, mood, tempo.
2 | Implement user interface for selecting preferences
3 | Research and implement a system for adjusting recommendations based on selected preferences
4 | Test customization options and adjust as necessary
5 | Develop system for refreshing customized recommendations periodically
6 | Implement a system for saving custom preferences for future recommendations
User story | As a user, I want to be able to listen to full tracks for recommeneded music | 21 | Fullstack Dev |  | 10h
1 | Research and intergrate a music streaming service or API
2 | Develop a system for tracking and logging user listetning history
3 | Implement a user interface for playing recommneded tracks
4 | Test music playback functionality and adjust as necessary
5 | Implement system for adding recommended tracks to user playlists
Develop a system for recommending similar tracks based on user listening history
User story | As a user, I want to be able to share my music recommendations with friends and on social media | 8 | Fullstack Dev | Not Started | 5h | [5 empty] | Pending
1 | Implement social media sharing functionality for recommended tracks
2 | Develop a system for generating shareable images for recommended tracks
3 | Test social media sharing functionality and adjust as necessary
4 | Implement system for sharing recommended tracks wit hfriends in-app
5 | Develop a system for generating shareable playlists
6 | Implement a social media sharing functionality for user playlists
User story | As a user, I want to be able to save my favorite tracks and view them later | 8 | Fullstack Dev | Not Started | 6h | [5 empty] | Pending
1 | Develop system for saving favorite tracks
2 | Implement user interface for viewing and managing favorite tracks
3 | Research and integrate a system for syncing favorite tracks across devices
4 | Test favorite track saving functionality and adjust as necessary
5 | Implement system for adding favorite tracks to user playlists
6 | Develop a system for recommending similar tracks based on user's favorite tracks
User story | As a user, I want to be able to search for specific tracks or artists | 3 | Fullstack Dev | Not Started | 2h | [5 empty] | Pending
1 | Research and integrate a music search API
2 | Implement user interface for music search
3 | Develop a system for displaying search results
4 | Test music search functionality and adjust as necesarry
5 | Implement system for adding searched tracks to suer playlists
6 | Develop a system for recommending similar tracks based on searched tracks or artists
User story | As a user, I want to be able to create and share playlists with friends and followers. | 13 | Fullstack Dev | Not Started | 7h | [5 empty] | Pending
1 | Determine playlists sharing options and implement sharing feature
2 | Design and implement playlist creation interface
3 | Integrate playlist functionality with social media platforms for sharing
4 | Test playlist sharing and ensure compatibility with different devices and operating systems
5 | Implement option for collaborative playlist creation with friends
6 | Ensure security and privacy measures for shared playlists
User story | As a user, I want to be able to follow and connect with other music enthusiasts. | 8 | Fullstack Dev | Not Started | 5h | [5 empty] | Pending
1 | Design and implement user profile and search functionality
2 | Implement option to follow other users and view their profiles
3 | Test and ensure compatibility with different devices and opearting systems
4 | Develop social features mesaures for user connections and interactions
5 | Implement algorithms to suggest music enthusiasts to follow
6 | Ensure privacy and securiy measures for user connections and interactions.
User story | As a user, I want to be able to discover new music and playlists based on what my friends and followers are listening to | 5 | Fullstack Dev | Not Started | 4h | [5 empty] | Pending
1 | Implement algorithm to suggest music based on user's friends and followers
2 | Design and implement personalized discovery section on the app
3 | Test and ensure compatibility with different devices and operating systems
4 | Test and ensure compatibiity with different devices and opearting systems
5 | Develop a way for users to easily save and add recommended music to their playlists
6 | Ensure privacy and security measures for recommended music
User story | As a user, I want to be able to share my favorite lyrics and quotes from songs on social media. | 13 | Fullstack Dev | Not Started | 7h | [5 empty] | Pending
1 | Design and implement a way for users to select and share lyrics or quotes from songs
2 | Develop social media sharing functionality for selected lyrics and quotes
3 | Ensure privacy and security measures for shared lyrics and quotes
4 | Test and ensure compatiblity with different devices and opearting systems
5 | Implement a way for users to easily discover and explore shared lyrics and quotes
6 | Allow users to save their favorite shared lyrics and quotes
User story | As a user I want to be able to collab with friends to create playlists and hsare music. | 3 | Fullstack Dev | Not Started | 3h | [5 empty] | Pending
1 | Implement collaborative playlists creation feature
2 | Allow users to invite friends to collab
3 | Ensure privacy and security measures for shared playlists and music
User story | As a user I want to be able to create and participate in music-related groups and events. | 8 | Fullstack Dev | Not Started | 8h | [5 empty] | Pending
1 | Design and implement groups and events sections on the app
2 | Allow users to create and join music-related groups and events
3 | Implement chat functionality for gorup discussions
4 | Develop a way for users to easily discover and join music-related events.
5 | Ensure privacy and security measures for groups and events
6 | Test and ensure compatibility with different devices and opearting systems
User story | As a user, I want to be able to create and customize my profile | 21 | Fullstack Dev | Not Started | 11h | [5 empty] | Pending
1 | Design and implement a user profile creation form
2 | Develop a backend system for storing user profile data
3 | Implement user profile customization options for profile picture, bio, and interests
4 | Develop a system for updating and saving user profile changes
5 | Test user profile creation and customization functionality
6 | Implement error handling for invalid or incomplete profile data
User story | As a user, I want to be able to connect wit hfriends and view their profiles | 13 | Fullstack Dev | Not Started | 6h | [5 empty] | Pending
1 | Develop a system for searching and adding friends to a user's friend list
2 | Implement user interface for viewing a friend's profile
3 | Develop a system for requesting and accepting friend requests
4 | Implement error handling for invalid or duplicate friend requests
5 | Test friend connection functionality
6 | Develop a system for displaying mutual friends between users
User story | As a user, I want to be able to manage my privacy settings | 13 | Fullstack Dev | Not Started | 6h | [5 empty] | Pending
1 | Design and implement a user interface for managing privacy settings
2 | Develop a backend system for storing privacy setting data
3 | Implement options for hiding or displaying profile information to specific users or groups
4 | Develop a system for revoking friend connections and blocking users
5 | Test privacy setting functionality
6 | Implement error handling for invalid or incomplete privacy settings
User story | As a user I want to be able to view and manage activity feed | 3 | Fullstack Dev | Not Started | 5h | [5 empty] | Pending
1 | Develop a system for tracking and storing user activity data
2 | Implement user interface for viewing activity feed
3 | Develop a system for filtering activity feed by type or date
4 | Implement user interface for deleting or hiding specific activites
5 | Test activity feed functionality
6 | Implement error handling for invalid or incomplete activity data
User story | As a user, I want to be able to view and manage my saved items | 5 | Fullstack Dev | Not Started | 4h | [5 empty] | Pending
1 | Design and implement a system for saving( e.g posts, playlists, events)
2 | Implement user interface for viewing saved items
3 | Develop a system for categorizing and organizing saved items
4 | Implement user interface for deleting or un-saving specific items
5 | Test saved item functionality
6 | Implement error handling for invalid or incomplete saved item data
User story | As a user, I want to be able to view and manage my notifications | 8 | Fullstack Dev | Not Started | 4h | [5 empty] | Pending
1 | Develop a system for tracking and sotring user notification data
2 | Implement user interface for viewing notifications
3 | Develop a system for filtering notifications by type or date
4 | Implement user interface for marking notifications as read or deleting them
5 | Test notification functionality
6 | Implement error handling for invalid or incomplete notification data